## Exhaustive feature list
Please Note: Deployed Features Will Be Visible Across All Business Units. Partial Deployment Is Not Feasible.
|  |  |  | Effort Estimation (in hours) |  |  | Trinity's perspective | Based on Time and Effort
Category | # | Features | Description | UI | Backend | DE/DS/GenAI | Feature Importance | Development Complexity | Trinity's Comments | Amgen's Comments
GenAI Model Upgrade | 1 | Archietectural Changes - Model Upgrade - GPT 4 Turbo | Upgrade the underlying architecture to GPT 4 Turbo with enhanced capabilities for generating responses. | NA | NA | 32 | Must Have | High
Strategies to Mitigate Latency | 2 | Predefine Responses for Organic Questions | Predefine responses for commonly asked organic questions to provide quicker and more consistent answers. |  |  |  | Good To have | Mid
| 3 | User Engagement - Real-time Backend Operation Status Display | Display real-time backend operation status to keep users informed about system performance and availability. |  |  |  | Good To have | High
| 4 | User Engagement - Live Streaming of Response Generation | Engage users by live streaming the response generation process, allowing them to see how answers are formed in real-time. |  |  |  | Good To have | High - Very High
| 5 | User Engagement - Source Display at the Beginning of Response Generation | Display the sources at beginning of response generation such that there will no user latency | 32 | 32 | 24 | Must Have | Mid - High | Displaying Sources while the response is being generated. Move the sources to the top of the response
| 6 | Multitasking: Chat Switching for Seamless Conversation Continuation | Allow users to seamlessly switch between multiple chats for uninterrupted conversation continuation. |  |  |  | Good To have | Mid
| 7 | Caching the Response | Cache responses to improve performance and reduce latency, ensuring quicker access to frequently requested information. |  |  |  | Good To have | High
Pubmed Use case | 8 | Pubmed Integration - showing relevant pubmed link from Knowledge base | Integrate with PubMed to display relevant articles from the Pubmed knowledge base | NA | NA | 40 | Good To have | UnKnown | Need clarity on pubmed use case | Deprioritize it
| 9 | Showing related article from pubmed (Customization) | Provide related articles from the PubMed directly |  |  |  | Good To have | UnKnown | Need clarity on pubmed use case
Response Type | 10 | Comparing the Uploaded vs Internal Knowledge base (Basic format) | Enable users to compare uploaded documents with the internal knowledge base in a basic format for content verification. | NA | NA | 32 | Must Have | High - Very High | Need Clarity on this use case with examples | Medical congess - What we know, what's new , Uplizna Example
Response Functionality Enhancement | 11 | Image based response - display image with response present in pdf Research article - Only Knowledge base | Extract relevant images from the article and display them alongside the response. |  |  |  | Good To have | Mid - High
| 12 | Image and link based output with response - to include Complex doc - PPT, Graph, Inforgraphics, Graphs etc. - Only Knowledge base | Enable inclusion of both images and links in responses from the knowledge base for complex documents such as videos, PowerPoint presentations, graphs, infographics, etc., which couldn't be parsed due to their high complexity. This provides users with supplementary visual content and direct access to the source material for further exploration. | 20 | 40 | 100 | Good To have | Mid - High | Need to do research , Investigate it through and Implement it in the Same Sprint
| 13 | Ability to Modify Response | Allow users to modify responses as needed for accuracy or customization. |  |  |  | Unknown | Mid
| 14 | Template based response - SRL etc. | Offer template-based responses, including SRL, to provide structured answers for specific types of queries. |  |  |  | Good To have | Mid (UnKnown)
Source citations | 15 | Truncate chunk in "+ more" and display only first two lines of chunk in the Source citations | Truncate lengthy chunks of text in "+ More" sections and display only the first two lines for improved readability. | 24 | NA | NA | Must Have | Mid - High |  | First three sources and view more
| 16 | Display sources document wise | Organize and display sources document-wise to provide users with a clear reference for each page.
| 17 | Display only sources from which response has been prepared | Show only the sources that were used to prepare a response
| 18 | Highlight chunk in the PDF | Highlight specific chunks of text in PDF documents for easier reference and analysis. |  |  |  | Good To have | Mid - High | Need to discuss the approach.
User Authentication | 19 | Okta Integration - Login with Okta button |  |  |  |  | Good To have | Mid - High
Scalable UI changes | 20 | Phase 1 - Tokens: Color, typography,spacing etc. Components: Buttons, text Field, card etc. themed Sections: landing page |  |  |  |  | Good To have | Mid - High
| 21 | Phase 2 - Components: Menu, Icons etc. Themed Sections: Feedback, Upload doc flow etc. Evolved Designs: Chat, Database selector etc. |  |  |  |  | Good To have | Mid - High | Need figma design for estimation
Chat functionality | 22 | Edit Chat title | Allow users to edit the title of a chat for better organization and context. |  |  |  | Good To have | Mid - High
| 23 | Next Query suggestions for Iterative Process Improvement | Follow-up Question Suggestions: Companion suggests follow-up questions to enhance user experience and foster an educational, iterative process.
| 24 | Delete Chat history | Enable users to delete chat history for privacy or organizational purposes. | 24 | 24 | NA | Must Have | Mid - High | Shall we also delete from the backend/our record? | Keep Role and Brand, TBD
Export Respone | 25 | Export response as PPT (Basic structure and content) | Provide the option to export responses as PowerPoint presentations with basic structure and content intact. | 16 | 16 | 24 | Good To have | High - Very High |  | Can Deprioritize it
| 26 | Export response as Excel | Allow users to export responses as Excel spreadsheets for further analysis and manipulation.
| 27 | Export response as Pdf/doc | Offer the ability to export responses as PDF or Word documents for easy sharing and offline access.
| 28 | Email insights/response to user group |  |  |  |  | Good To have | High - Very High
Import Functionality | 29 | Upload docx |  | 12 | 12 | 24 | Must Have | Mid - High
| 30 | Upload PPT
| 31 | Upload Handwritten notes |  |  |  |  | Good To have | Mid - High
| 32 | Increase upload limit by size | Increase the upload limit for documents by size accommodate larger files | [6 empty] | Can think about it
| 33 | Increase upload limit # docs | Increase the upload limit for documents by number to accommodate multiple uploads. | NA | NA | 32 | Must Have | High |  | Can Deprioritize it
Application Accessibility | 34 | Ability to access application on Iphone, Ipad, Tablets etc. | Ensure compatibility with mobile devices such as iPhones, iPads, and tablets for convenient access to the application. | Can't evaluate | NA | NA | Good To have | Mid - High | Need Figma design for other devices.
Application to Companion Admin Portal | 35 | View/Add/delete user and change BU | Independent Basic Application |  |  |  | Good To have | Mid - High
| 36 | View/Add/delete Knowledge base document |  |  |  |  | Good To have | Mid - High
Application tracking system | 37 | Automated User Report Generation and Distribution to Administrators |  |  |  |  | Good To have | High - Very High
| 38 | Application/BI Dashboard for Real-time Application Utilization Monitoring | Develop a dashboard for real-time monitoring of application utilization and performance metrics, facilitating data-driven decision-making. |  |  |  | Good To have | High
| 39 | Application for Tracking User Feedback and Troubleshooting GenAI Operations | Create an application for tracking user feedback and troubleshooting GenAI operations to continuously improve user experience and system efficiency. | NA | NA | 32 | Must Have | High | Need to discuss the tech requirements
Notification Model | 40 | Notify the user of any enhancement |  | 128 | 124 | 340
| 41 | Notify the user if BU has added |  | 16 | 15.5 | 42.5
| 42 | Notify user if knowledge base has updated |  | 0.8 | 0.775 | 2.125

## Sprint 4 timeline
Features | UI | Backend | DE/DS/GenAI | W1 | W2 | W3 | W4
Archietectural changes - Model Upgrade - GPT 4 Turbo | NA | NA | 32
User Engagement - Source Display at the Beginning of Response Generation | 32 | 32 | 24
Image and link based output with response - to include Complex doc - PPT, Graph, Inforgraphics, Graphs etc. - Only Knowledge base | 20 | 40 | 80
Roll up the chunk in more and display if click on more | 24 | NA | NA
Pubmed Integration - showing relevant pubmed link from Knowledge base | NA | NA | 40
Comparing the Uploaded vs Internal Knowledge base (Basic format) | NA | NA | 32
Delete Chat history | 24 | 24 | NA
Export response as PPT (Basic structure and content) | 16 | 16 | 24
Upload docx | 12 | 12 | 24
Increase upload limit # docs/Size | NA | NA | 32
Application for Tracking User Feedback and Troubleshooting GenAI Operations | NA | NA | 32
Deployment to Production
Total Hours | 128 | 124 | 320
Total days | 16 | 15.5 | 40
Resources | 0.8 | 0.775 | 2

## Companion Admin Portal
Companion Admin Portal |  |  |  |  | Companion Admin Portal |  |  |  |  | Companion Admin Portal
User Access Management |  |  |  |  | User Access Management |  |  |  |  | User Access Management
Knowledge Base Management | View User List | Add User | Delete User | Change BU | Knowledge Base Management | View User List | Add User | Delete User | Change BU | Knowledge Base Management | View User List | Add User | Delete User | Change BU
| # | User Name | Email ID | BU
| 1 | Abhay Patel | apatel27@amgen.com | TEPEZZA |  | Name |  |  |  |  | Email ID |  |  | View
| 2 | Vinaya Shankara | vshank02@amgen.com | UPLIZNA
| 3 | Nikunj Aggarwal | naggar02@amgen.com | TEPEZZA |  | Email ID |  |  |  |  | # | User Name | Email ID | BU
| 4 | Krishna Shukla | kshukl03@amgen.com | TEPEZZA | [6 empty] | 1 | Abhay Patel | apatel27@amgen.com | TEPEZZA
| 5 | Deepti Yadav | Dyadav07@amgen.com | TEPEZZA |  | Business Unit
[7 empty] | Add |  |  |  |  | Delete

## Screenshot
Feature no : 3 , User Engagement - Real-time Backend Operation Status Display | Feature no : 5 , User Engagement - Source Display at the Beginning of Response Generation | Feature no : 12 , Image and link based output with response - to include Complex doc - PPT, Graph, Inforgraphics, Graphs etc. - Only Knowledge base | Feature no : 15 , Display sources document wise | Feature no : 16 , Display sources document wise | Feature no : 23, Next Query suggestions for Iterative Process Improvement
https://www.phind.com/search?home=true